## Gantt Plan
WBS | ID | Parent | Type | Name | Start | End | Duration (days) | Progress % | Status | Priority | Resources | Color | Style
1 | 1 |  | Project | SAP S/4HANA Global Transformation | 2026-01-01 | 2027-06-30 | 546 | 3 | In Progress | High | Programme Director | #1F4E79 | Bold
1.1 | 2 | 1 | Phase | Discover & Prepare | 2026-01-01 | 2026-03-31 | 90 | 100 | Completed | High | PMO | #4F81BD | Normal
1.1.1 | 3 | 2 | Workstream | Project Management | 2026-01-01 | 2026-03-31 | 90 | 100 | Completed | High | Project Manager | #9DC3E6 | Normal
1.1.1.1 | 4 | 3 | Activity | Governance & Control | 2026-01-01 | 2026-03-31 | 90 | 100 | Completed | High | PMO | #BDD7EE | Normal
1.1.1.1.1 | 5 | 4 | Task | Establish Steering Committee | 2026-01-01 | 2026-01-15 | 15 | 100 | Completed | High | Programme Director | #BDD7EE | Normal
1.1.1.1.2 | 6 | 4 | Task | Weekly Status Reporting | 2026-01-15 | 2026-03-31 | 76 | 75 | In Progress | High | PMO | #BDD7EE | Normal
1.1.1.2 | 7 | 3 | Activity | Financial Control | 2026-01-01 | 2026-03-31 | 90 | 60 | In Progress | High | Finance Lead | #BDD7EE | Normal
1.1.1.2.1 | 8 | 7 | Task | Budget Tracking | 2026-01-01 | 2026-03-31 | 90 | 60 | In Progress | High | Finance Team | #BDD7EE | Normal
1.1.1.2.2 | 9 | 7 | Task | Forecast Updates | 2026-02-01 | 2026-03-31 | 59 | 50 | In Progress | Medium | Finance Team | #BDD7EE | Normal
1.1.2 | 10 | 2 | Workstream | Functional | 2026-04-01 | 2026-07-31 | 122 | 60 | In Progress | High | Functional Leads | #C6E0B4 | Normal
1.1.2.1 | 11 | 10 | Activity | Fit-to-Standard Workshops | 2026-04-01 | 2026-05-31 | 61 | 90 | In Progress | High | Functional Team | #C6E0B4 | Normal
1.1.2.1.1 | 12 | 11 | Task | Finance Workshops | 2026-04-01 | 2026-04-20 | 20 | 100 | Completed | High | FI Lead | #C6E0B4 | Normal
1.1.2.1.2 | 13 | 11 | Task | Procurement Workshops | 2026-04-15 | 2026-05-10 | 26 | 100 | Completed | High | MM Lead | #C6E0B4 | Normal
1.1.2.1.3 | 14 | 11 | Task | Sales Workshops | 2026-05-01 | 2026-05-31 | 31 | 90 | In Progress | High | SD Lead | #C6E0B4 | Normal
1.1.2.2 | 15 | 10 | Activity | System Configuration | 2026-08-01 | 2026-11-30 | 122 | 10 | In Progress | High | Functional Team | #C6E0B4 | Normal
1.1.2.2.1 | 16 | 15 | Task | Configure Finance | 2026-08-01 | 2026-08-31 | 31 | 0 | Not Started | High | FI Consultant | #C6E0B4 | Normal
1.1.2.2.2 | 17 | 15 | Task | Configure Procurement | 2026-09-01 | 2026-09-30 | 30 | 0 | Not Started | High | MM Consultant | #C6E0B4 | Normal
1.1.2.2.3 | 18 | 15 | Task | Configure Sales | 2026-10-01 | 2026-10-31 | 31 | 0 | Not Started | High | SD Consultant | #C6E0B4 | Normal
1.1.2.2.4 | 19 | 15 | Task | RICEFW Development | 2026-08-01 | 2026-11-30 | 122 | 5 | In Progress | High | ABAP Team | #C6E0B4 | Normal
1.1.3 | 20 | 2 | Workstream | Data Migration | 2026-05-01 | 2027-03-31 | 335 | 25 | In Progress | High | Data Lead | #F8CBAD | Normal
1.1.3.1 | 21 | 20 | Activity | Data Strategy | 2026-05-01 | 2026-06-30 | 61 | 100 | Completed | High | Data Architect | #F8CBAD | Normal
1.1.3.1.1 | 22 | 21 | Task | Define Data Objects | 2026-05-01 | 2026-05-15 | 15 | 100 | Completed | High | Data Team | #F8CBAD | Normal
1.1.3.1.2 | 23 | 21 | Task | Data Cleansing Plan | 2026-05-15 | 2026-06-30 | 46 | 100 | Completed | High | Business Data Owners | #F8CBAD | Normal
1.1.3.2 | 24 | 20 | Activity | Mock Migrations | 2026-10-01 | 2027-01-31 | 123 | 0 | Not Started | High | Data Team | #F8CBAD | Normal
1.1.3.2.1 | 25 | 24 | Task | Mock 1 | 2026-10-01 | 2026-10-31 | 31 | 0 | Not Started | High | Data Team | #F8CBAD | Normal
1.1.3.2.2 | 26 | 24 | Task | Mock 2 | 2026-12-01 | 2026-12-31 | 31 | 0 | Not Started | High | Data Team | #F8CBAD | Normal
1.1.3.2.3 | 27 | 24 | Task | Mock 3 | 2027-01-01 | 2027-01-31 | 31 | 0 | Not Started | High | Data Team | #F8CBAD | Normal
1.1.4 | 28 | 2 | Workstream | Integration | 2026-05-01 | 2026-12-31 | 245 | 30 | In Progress | High | Integration Lead | #D9E1F2 | Normal
1.1.4.1 | 29 | 28 | Activity | Interface Design | 2026-05-01 | 2026-06-30 | 61 | 100 | Completed | High | Integration Architect | #D9E1F2 | Normal
1.1.4.1.1 | 30 | 29 | Task | Identify Interfaces | 2026-05-01 | 2026-05-20 | 20 | 100 | Completed | High | Integration Team | #D9E1F2 | Normal
1.1.4.1.2 | 31 | 29 | Task | Define Interface Specs | 2026-05-15 | 2026-06-30 | 46 | 100 | Completed | High | Integration Team | #D9E1F2 | Normal
1.1.4.2 | 32 | 28 | Activity | Interface Build & Test | 2026-08-01 | 2026-11-30 | 122 | 5 | In Progress | High | Integration Dev Team | #D9E1F2 | Normal
1.1.4.2.1 | 33 | 32 | Task | Develop Interfaces | 2026-08-01 | 2026-10-31 | 92 | 10 | In Progress | High | Developers | #D9E1F2 | Normal
1.1.4.2.2 | 34 | 32 | Task | Interface SIT | 2026-11-01 | 2026-11-30 | 30 | 0 | Not Started | High | Test Team | #D9E1F2 | Normal
1.1.5 | 35 | 2 | Workstream | Testing | 2026-10-01 | 2027-03-31 | 182 | 0 | Not Started | High | Test Manager | #FFF2CC | Normal
1.1.5.1 | 36 | 35 | Activity | System Integration Testing | 2026-10-01 | 2026-11-30 | 61 | 0 | Not Started | High | Test Team | #FFF2CC | Normal
1.1.5.1.1 | 37 | 36 | Task | SIT Finance | 2026-10-01 | 2026-10-15 | 15 | 0 | Not Started | High | Test Team | #FFF2CC | Normal
1.1.5.1.2 | 38 | 36 | Task | SIT Procurement | 2026-10-16 | 2026-10-30 | 15 | 0 | Not Started | High | Test Team | #FFF2CC | Normal
1.1.5.2 | 39 | 35 | Activity | User Acceptance Testing | 2027-02-01 | 2027-02-28 | 28 | 0 | Not Started | High | Business Users | #FFF2CC | Normal
1.1.5.2.1 | 40 | 39 | Task | UAT Finance | 2027-02-01 | 2027-02-14 | 14 | 0 | Not Started | High | Business Users | #FFF2CC | Normal
1.1.5.2.2 | 41 | 39 | Task | UAT Procurement | 2027-02-15 | 2027-02-28 | 14 | 0 | Not Started | High | Business Users | #FFF2CC | Normal
1.1.6 | 42 | 2 | Workstream | Cutover | 2027-01-01 | 2027-03-31 | 90 | 0 | Not Started | Critical | Cutover Manager | #C00000 | Normal
1.1.6.1 | 43 | 42 | Activity | Cutover Planning | 2027-01-01 | 2027-01-31 | 31 | 0 | Not Started | High | Cutover Team | #C00000 | Normal
1.1.6.1.1 | 44 | 43 | Task | Cutover Plan Creation | 2027-01-01 | 2027-01-15 | 15 | 0 | Not Started | High | Cutover Lead | #C00000 | Normal
1.1.6.1.2 | 45 | 43 | Task | Cutover Rehearsal | 2027-01-15 | 2027-01-31 | 16 | 0 | Not Started | High | Cutover Team | #C00000 | Normal
1.1.6.2 | 46 | 42 | Activity | Go-Live Execution | 2027-03-01 | 2027-03-01 | 1 | 0 | Not Started | Critical | All Teams | #C00000 | Bold

## Dependencies
WBS From | Task From | WBS To | Task To | Type