## Lvl 1 Release Plan
LEVEL 1 PLAN - Weekly / Monthly | [11 empty] | Not Started
In Progress
At Risk
Delayed
Completed
[12 empty] | Milestone | X
|  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
| Programme / Release / Project / Phase/. Milestone | 2026-03-01 | 2026-03-08 | 2026-03-15 | 2026-03-22 | 2026-03-29 | 2026-04-05 | 2026-04-12 | 2026-04-19 | 2026-04-26 | 2026-05-03 | 2026-05-10 | 2026-05-17 | 2026-05-24 | 2026-05-31 | 2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-28 | 2026-07-05 | 2026-07-12 | 2026-07-19 | 2026-07-26 | 2026-08-02 | 2026-08-09 | 2026-08-16 | 2026-08-23 | 2026-08-30 | 2026-09-06 | 2026-09-13 | 2026-09-20 | 2026-09-27 | 2026-10-04 | 2026-10-11 | 2026-10-18 | 2026-10-25 | 2026-11-01 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-11-29
Release / Project 1
Discovery | bar: 2026-03-08 to 2026-03-29
- Milestone - Finalise Scope | bar: 2026-03-22
Design | bar: 2026-03-29 to 2026-04-19
Build | bar: 2026-04-26 to 2026-05-17
Test | bar: 2026-05-24 to 2026-06-14
Deploy | bar: 2026-06-21 to 2026-07-12
- Milestone - Go Live | bar: 2026-07-12
Support | bar: 2026-07-19 to 2026-08-09
Release / Project 2
Discovery | bar: 2026-04-05 to 2026-04-19
Design | bar: 2026-04-26 to 2026-05-17
Build | bar: 2026-05-24 to 2026-06-14
Test | bar: 2026-06-21 to 2026-07-12
Deploy | bar: 2026-07-19 to 2026-08-09
- Milestone - Go Live | bar: 2026-08-16
Support | bar: 2026-08-16 to 2026-09-06
Release / Project 3
Discovery | bar: 2026-05-03 to 2026-05-17
Design | bar: 2026-05-24 to 2026-06-14
Build | bar: 2026-06-21 to 2026-07-12
Test | bar: 2026-07-19 to 2026-08-09
Deploy | bar: 2026-08-16 to 2026-09-13
Support | bar: 2026-09-13 to 2026-10-04

## Activity Plan
Daily / Weekly Plan
High Level Plan - By Activity
| January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November
Project / Release / Phase or Environment | time axis 2025-12-30 to 2026-11-17
Release 1 / Project 1
DEV (Development) | 2025-12-30: INST; 2026-01-06: HLD; 2026-01-13: HLD; 2026-01-20: LLD; 2026-01-27: LLD; 2026-02-03: Bld; 2026-02-10: Bld; 2026-02-24: UT
QAS (Quality Assurance) | 2026-02-17: Data; 2026-03-03: SIT; 2026-03-10: UAT; 2026-03-17: UAT; 2026-03-24: UT
PRD (Production) | 2026-03-31: Cutover; 2026-04-07: HC
Release 2 / Project 2
Design / Build | 2026-02-03: INST; 2026-02-10: HLD; 2026-02-17: HLD; 2026-02-24: LLD; 2026-03-03: LLD; 2026-03-10: Bld; 2026-03-17: Bld; 2026-03-31: UT
Test / Train | 2026-03-24: Data; 2026-04-07: SIT; 2026-04-14: UAT; 2026-04-21: UAT; 2026-04-28: UT
Cutover / Deploy | 2026-05-05: Cutover; 2026-05-12: HC
Release 3 / Project 3
DEV (Development) | 2026-04-28: INST; 2026-05-05: HLD; 2026-05-12: HLD; 2026-05-19: LLD; 2026-05-26: LLD; 2026-06-02: Bld; 2026-06-09: Bld; 2026-06-23: UT
QAS (Quality Assurance) | 2026-06-16: Data; 2026-06-30: SIT; 2026-07-07: UAT; 2026-07-14: UAT; 2026-07-21: UT
PRD (Production) | 2026-07-28: Cutover; 2026-08-04: HC
Key - Activity Library
|  | Dis | Discovery
|  | HLD | High Level Design
|  | LLD | Low Level Design
|  | Bld | Build
|  | Data | Data Migration
|  | INST | Software Installation
|  | COPY | System Copy
|  | SIT | System Integration Testing
|  | UT | Unit Testing
|  | UAT | User Acceptance Testing
|  | OAT | Operational Acceptance Testing
|  | UT | User Training
|  | Cutover | Cutover
|  | HC | Hypercare
|  | CR 1 | Change Request 1
|  | CR 2 | Change Request 2