## Project Status Report Template
Project Name | Project X |  | PM Name | Peter Voss |  |  | W/C: | 2019-09-02
PRID | ?? |  | Portfolio: | S/4 Hana | C/4 Hana | Success Factors
Milestones | Discover | Prepare | Explore | Realise | Deploy | Run | Service Transition | Close
Forecast Date | 2019-09-11 | 2019-09-12 | 2019-09-30 | 2019-10-10 | 2019-10-25 | 2019-11-15 | 2019-12-03 | 2019-02-15
Actual Date | Draft | Draft | Draft | Draft | Draft | Draft | Draft | Draft
This Week’s Overall RAG | This Week’s RAG by Type | RAG Type | Last Week’s RAG by Type | Last Week’s Overall RAG | Achievements Planned for Next Period
A | A | Budget | G | G | 1. aaa |  |  |  | R
| R | Resource | G |  | 2. aaa |  |  |  | A
| G | Schedule | G |  | 3. aaa |  |  |  | G
| A | Quality | G |  | 4. aaa |  |  |  | Grey
Project Summary / RAG Commentary |  |  |  |  | Last Gate Passed: | Date passed: | Next Gate(s): | Date Scheduled:
• Scope … |  |  |  |  | Discover | n/a | Prepare | 2019-09-11
• Scope … |  |  |  |  | Prepare | n/a | Explore | TBC
• Budget … |  |  |  |  | Explore | n/a | Realise | TBC
• Resources … |  |  |  |  | Realise | n/a | Deploy | TBC
• Schedule … |  |  |  |  | Deploy | n/a | Run | TBC
• Quality … |  |  |  |  | Run | n/a | Close | TBC
Achievements this Period |  |  |  | ID, Risk / Issue |  |  | Owner | RAG
• …. |  |  |  | • I: |  |  |  | A
• …. |  |  |  | • I: |  |  |  | G
• …. |  |  |  | • I: |  |  |  | G
• …. |  |  |  | • I: |  |  |  | R
• …. |  |  |  | • R: |  |  |  | G
• …. |  |  |  | • R: |  |  |  | G
• …. |  |  |  | • R: |  |  |  | G
• |  |  |  | • R: |  |  |  | G
Achievements Planned but not achieved this Period |  |  |  | Financial Summary
• |  |  |  | Baseline Budget (A) | Cost To Date (B) | Cost to Complete (C) | Forecast Total Cost | Variance to Baseline
• |  |  |  | 1000 | 600 | 500 | 1100 | -100
•
Reporting Period | 2019-09-03 | 2019-09-10 | 2019-09-17 | 2019-09-24 | 2019-10-01 | 2019-10-08 | 2019-10-15 | 2019-10-22
Overall RAG | bar: 2019-09-03 to 2019-10-22